## Sheet1
Project Title |  | Start Date |  |  |  |  | Project Duration
Website for NANN MOTORS shop |  | 2024-09-06 |  |  |  |  | 71
Project Manager |  | End Date
KEG/IT/2324/F/209 |  | 2024-12-15
# | Task | Start Date | End Date | Duration | Task Status | Remarks
1 | Created project proposal video and project proposal | 2024-09-06 | 2024-09-08 | 2 | Completed |  |  | Complete | 1
2 | Learn HTML,CSS & JS | [6 empty] | In Progress | 2
2.1 | HTML | 2024-09-09 | 2024-09-16 | 6 | In Progress |  |  | Not Started | 9
2.2 | CSS | 2024-09-17 | 2024-09-24 | 6 | In Progress
2.3 | JavaScript | 2024-09-25 | 2024-10-02 | 6 | Not Started
3 | Gathering Requirements for the website
3.1 | Bike brands | 2024-10-03 | 2024-10-06 | 3 | Not started
3.2 | Prices | 2024-10-06 | 2024-10-09 | 3 | Not started
4 | Creating the layout of the website | 2024-09-10 | 2024-10-24 | 14 | Not Started
5 | Designing the graphics and edits required for the website | 2024-10-25 | 2024-11-15 | 21 | Not Started
6 | Coding
6.1 | Creating HTML Coding | 2024-11-16 | 2024-11-23 | 7 | Not Started
6.2 | Creating JS Coding | 2024-11-24 | 2024-12-01 | 7 | Not Started
6.3 | Style through CSS | 2024-12-02 | 2024-12-09 | 7 | Not Started
7 | Finalize and prepare the presentation | 2024-12-10 | 2024-12-15 | 5 | Not Started
Formulas:
Project Duration = NETWORKDAYS([Start Date],G8)
Duration = NETWORKDAYS([Start Date],[End Date])